## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
gbXaFDIzoECF1s_m8aI-SckADXRY | Collected soil samples from cashew fields | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 01/22/2026 |  | false | false | 2026-04-30 | MITHUSHH P it22180902
LHLZav-LGUuF8oi_UJhLCMkAF8y_ | Tested soil pH and moisture levels | Closing | Completed | High | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 01/14/2026 |  | false | false | 2026-05-01 | MITHUSHH P it22180902
Qsx9HZGEzkmU4mf6GtCsGckAGY8a | Prepared soil health analysis report | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 09/09/2025 |  | false | false | 2026-05-02 | MITHUSHH P it22180902
Dq_SVXkyc0qA55-vy6YOxckACkmC | Studied basics of IoT architecture | Closing | Completed | High | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 08/20/2025 |  | false | false | 2026-05-03 | MITHUSHH P it22180902
RAs5KE4UjEWuHE5yZHcF_skANe0X | Researched soil monitoring sensors | Closing | Completed | Low | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 08/19/2025 |  | false | false | 2026-05-04 | MITHUSHH P it22180902
0LwSpKlapEuUMZ9MDgg8HckAIZlL | Learned Arduino basics | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 08/05/2025 |  | false | false | 2026-05-05 | MITHUSHH P it22180902
wFvL_3VEaECS9EUhU6xx5ckACAq5 | Studied ESP32 module | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 08/06/2025 |  | false | false | 2026-05-06 | MITHUSHH P it22180902
ICieNQXor0alvpjIFkBJlMkAKpa_ | Collected dataset for training | Closing | Completed | High | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 10/15/2025 |  | false | false | 2026-05-07 | MITHUSHH P it22180902
74ITIg_vxkWHyh8oT8CDjskAAYwu | Chose suitable ML algorithm | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 11/04/2025 |  | false | false | 2026-05-08 | MITHUSHH P it22180902
jarungEZBEyrHahKJB6O_ckADiNT | Trained model on dataset | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 12/08/2025 |  | false | false | 2026-05-09 | MITHUSHH P it22180902
kxE0hVVLG02kUiuCQ1Hq68kAGz93 | Identified common cashew pests | Closing | Completed | Low | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 03/31/2026 |  | false | true | 2026-05-10 | USMAN M.H it22351104
ynAyIUgEhECJlCW00sA1r8kALdq2 | Researched pest behavior and lifecycle | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 03/24/2026 |  | false | true | 2025-05-11 | USMAN M.H it22351104
jWCd1ucM00usxvaBo8N-rckAHK-s | Monitored pest activity in field | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 03/25/2026 |  | false | true | 2025-05-12 | USMAN M.H it22351104
kaSus9yg0kCordIsJlHtBskAHGuy | Collected pest image dataset | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 09/24/2025 |  | false | true | 2026-05-13 | USMAN M.H it22351104
Z61INcta8k6prhvTV0T_kskABcKI | Labeled pest images | Closing | Completed | High | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 10/22/2025 |  | false | true | 2026-05-14 | USMAN M.H it22351104
9qB8WDX5lEi-EqKb89JZhskAMdOP | Cleaned and prepared dataset | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 09/25/2025 |  | false | true | 2026-05-15 | USMAN M.H it22351104
NWgnCykO60OxkrYzWT0fB8kAHJvH | Split data into train and test sets | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 10/25/2025 |  | false | true | 2026-05-16 | USMAN M.H it22351104
wRdNGWAeYEaMFfsQSkYha8kAFM1T | Trained model on pest images | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 11/13/2025 |  | false | true | 2026-05-17 | USMAN M.H it22351104
L0gTYqrnBki1fRVHnd04tckAI8HE | Evaluated model accuracy | Closing | Completed | High | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 02/19/2026 |  | false | true | 2026-05-18 | USMAN M.H it22351104
eb1jPCBWw0qKCxGl0lEdaskAJzHX | Evaluated model accuracy | Closing | Completed | Medium | MITHUSHH P it22180902 | MITHUSHH P it22180902 | 04/30/2026 | 11/28/2025 |  | false | false | 2026-05-19 | MITHUSHH P it22180902
g7TXAN7TYUev0uF_lVSTFckAJXJc | Tested model with new images | Closing | Completed | Medium | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 05/20/2026 |  | false | false | 2026-05-20 | USMAN M.H it22351104
e6K-dRPBlkW8HTQyMOwmSskAAQ9u | Classified pest types | Closing | Completed | High | USMAN M.H it22351104 | USMAN M.H it22351104 | 04/30/2026 | 09/17/2025 |  | false | true | 2026-05-21 | USMAN M.H it22351104
Pt6FQN0X6ECVryFQuWpPDckAGu0O | Studied cashew grading standards | Closing | Completed | Low | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 11/19/2025 |  | false | false | 2026-05-22 | SANOCH M it22159694
gD9_IkiNWUCe9WLSYYGv1skANwUq | Identified grading parameters | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 10/15/2025 |  | false | false | 2026-05-23 | SANOCH M it22159694
Jf5PtwQnbkWMN57Ujo7K-8kAKgKn | Sorted nuts by size | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 09/17/2025 |  | false | false | 2026-05-24 | SANOCH M it22159694
cQ18_aZ81US_JGr8LzjokMkAA1Lh | Removed defective nuts | Closing | Completed | High | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 |  |  | false | false | 2026-05-25 | SANOCH M it22159694
M4ivgHKfOEurDDUfqdrEY8kALj4n | Classified grades manually | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 09/08/2025 |  | false | false | 2026-05-26 | SANOCH M it22159694
uz4CVkltS0iyrCM6GjGOdskAHM2X | Built grading model | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 10/09/2025 |  | false | false | 2026-05-27 | SANOCH M it22159694
onnr1NkBu0ysJtRfdtWxlskAHObQ | Tested grading accuracy | Closing | Completed | Low | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 11/13/2025 |  | false | false | 2026-05-28 | SANOCH M it22159694
gP3RwWS6SU-pfnKRk_bJZckAHgAy | Compared manual vs model grading | Closing | Completed | Low | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 01/21/2026 |  | false | false | 2026-05-29 | SANOCH M it22159694
Rw-rwfAHz0KWrWY1t2iFyskAIyDH | Classified cashews using model | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 12/16/2025 |  | false | false | 2026-05-30 | SANOCH M it22159694
hHhpuO0M60eASDatSIW3TMkAPSp2 | Integrated grading with system | Closing | Completed | Medium | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 01/05/2026 |  | false | false | 2026-05-31 | SANOCH M it22159694
_fNBqr7d10-Z8hWynXT3SMkAOwDb | Recorded grading results | Closing | Completed | High | SANOCH M it22159694 | SANOCH M it22159694 | 04/30/2026 | 02/11/2026 |  | false | false | 2026-06-01 | SANOCH M it22159694
l8F4aNpiPEy7JBxM2K9_MskAAFRL | Identified common leaf diseases | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 02/18/2026 |  | false | true | 2026-06-02 | THIMOTHY K L it22206428
Vg6IZ1bfoE2n_uxRN-U5NMkAJOZO | Collected leaf image samples | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 09/18/2025 |  | false | true | 2026-06-03 | THIMOTHY K L it22206428
5AtoVoMdGUKHiL5Mn2gK4ckAPgeo | Captured healthy and diseased leaves | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 02/17/2026 |  | false | true | 2026-06-04 | THIMOTHY K L it22206428
NQftaMaAJUGcmLMYpyncWMkAMVo_ | Labeled leaf images | Closing | Completed | Low | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 08/19/2025 |  | false | true | 2026-06-05 | THIMOTHY K L it22206428
b1dNtp-eLk6IOOjX9KJlzskAIEzY | Cleaned and prepared dataset | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 09/23/2025 |  | false | true | 2026-06-06 | THIMOTHY K L it22206428
pazmeMN9MEGBwRwhsP2TQMkAH12d | Augmented image data | Closing | Completed | High | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 10/21/2025 |  | false | true | 2026-06-07 | THIMOTHY K L it22206428
DusEP97htEGV7DupHknBGskAJwMz | Built CNN model | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 11/26/2025 |  | false | true | 2026-06-08 | THIMOTHY K L it22206428
l2knNoleFEy5BWOZHWxA98kADDe_ | Trained model on leaf images | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 10/23/2025 |  | false | true | 2026-06-09 | THIMOTHY K L it22206428
FENGjsXNJ0y6exhZV7VeDskAEnPL | Detected disease using model | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 02/10/2026 |  | false | true | 2026-06-10 | THIMOTHY K L it22206428
C2r-MiiE_kCLisvbJHVcCckAAvg0 | Classified disease types | Closing | Completed | High | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 01/21/2026 |  | false | true | 2026-06-11 | THIMOTHY K L it22206428
xfVGQ3gkrESGS8EluSeG78kALkJX | Integrated model with system | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 11/20/2025 |  | false | true | 2026-06-12 | THIMOTHY K L it22206428
awwhnE2-cka6aWtBGHckqckAG_OK | Improved model performance | Closing | Completed | Medium | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 11/19/2025 |  | false | true | 2026-06-13 | THIMOTHY K L it22206428
ibDpIX30dUGyfazJc3VcxMkAHQAB | Documented disease detection process | Closing | Completed | Low | THIMOTHY K L it22206428 | THIMOTHY K L it22206428 | 04/30/2026 | 03/17/2026 |  | false | false | 2026-06-14 | THIMOTHY K L it22206428

## Plan name
Plan name | Cashew Sense
Plan ID | sPkxCYZ_0UiKg6Lnn1St1MkABa0j
Date of export | 05/01/2026